## Project Timeline
PROJECT TIMELINE
PROJECT TITLE |  | Enhancing the digital competencies and entrepreneurship skills of academic musicians in Serbia for culturally more engaged society – DEMUSIS
PROJECT MANAGER |  | Ivana Perković |  | START DATE | [6 empty] | 2019-01-15
WP |  |  | ACTIVITY | Y1 | [11 empty] | Y2 | [11 empty] | Y3 | [11 empty] | Y4
| PROJECT MONTH: |  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12
WP 1 | Preparation and Analysis |  | WP 1.1.Current national study programmes analyzed, reviewed and compared with similar EU programmes | bar: Y1 M2 to Y2 M5
WP 1.2. Study visits to EU Higher education institutions | bar: Y1 M2 to Y1 M12
WP 1.3. Learning outcomes and competences defined | bar: Y1 M2 to Y1 M6
WP 1.4. Current study programmes modernized and adopted | bar: Y1 M2 to Y1 M9
WP 1.5. New study programs designed and accredited | bar: Y1 M2 to Y2 M10; Y3 M10 to Y4 M1
WP 2 | Upgrading of methodology |  | WP 2.1 Equipment purchase plan | bar: Y1 M2 to Y1 M6
WP 2.2. Hardware purchase | bar: Y1 M6 to Y2 M9; Y3 M8 to Y3 M9
WP 2.3 Software purchase | bar: Y1 M6 to Y2 M9
WP 2.4 Development of adequate infrastructure | bar: Y1 M8 to Y1 M12
WP 2.5 Equipment installation and set-up | bar: Y1 M8 to Y2 M11
WP 2.6 Creation of distance learning platform | bar: Y1 M3; Y1 M10 to Y3 M1
WP 3 | Staff training and development of teaching resources |  | WP 3.1 Teachers training for curricular changes and LLL courses | bar: Y2 M3 to Y3 M3; Y3 M5; Y3 M10 to Y3 M12; Y4 M3 to Y4 M4; Y4 M9
WP 3.2 Teacher and staff training for distance learning and LoLa equipment | bar: Y2 M2 to Y3 M1
WP 3.3 Teaching materials' development and publishing | bar: Y2 M2 to Y3 M12
WP 3.4 Preparation of online courses | bar: Y2 M2 to Y4 M5
WP 4 | Implementation of reformed and new study programs |  | WP 4.1 Student enrollment to modernized study program | bar: Y1 M9 to Y1 M10; Y2 M9 to Y2 M10; Y3 M9 to Y3 M10; Y4 M9 to Y4 M10
WP 4.2 Student enrollment to new study programs | bar: Y2 M9 to Y2 M10; Y3 M9 to Y3 M10; Y4 M9 to Y4 M10
WP 4.3 Implementation of modernized and new study programs | bar: Y1 M10 to Y4 M12
WP 4.4 Implementation of online courses | bar: Y2 M3 to Y4 M12
WP 4.5 Student placements | bar: Y3 M2 to Y3 M12; Y4 M3 to Y4 M10
WP 5 | LLL courses development and implementation |  | WP 5.1 LLL courses design and accreditation | bar: Y3 M4 to Y4 M9
WP 5.2 Preparation of LLL courses learning materials | bar: Y3 M10 to Y4 M9
WP 5.3 Implementation of LLL courses | bar: Y4 M9 to Y4 M12
WP 6 | Quality control and monitoring |  | WP 6.1 Quality Assurance Group
WP 6.2 Project Quality Action Plan | bar: Y1 M4 to Y2 M2
WP 6.3 Internal Quality Procedures
WP 6.4 External Quality Procedures
WP 7 | Dissemination and exploitation plan |  | WP 7.1 Dissemination and exploitation plan | bar: Y1 M2 to Y2 M8
WP 7.2 Project website, social media engagemenet
WP 7.3 Academic and financial sustainability plan | bar: Y2 M12 to Y3 M11
WP 7.4 Preparation of promotional materials
WP 7.5 Promotional activities | bar: Y1 M1 to Y4 M12
WP 7.6 Student projects made public | bar: Y3 M4 to Y3 M6; Y4 M4 to Y4 M10
WP 7.7 Public debate in Novi Sad, European Capital of Culture | bar: Y4 M8 to Y4 M10
WP 8 | Management |  | WP 8.1 Kick-off meeting | bar: Y1 M2
WP 8.2 Establishment of Project Management Board | bar: Y1 M2; Y2 M11
WP 8.3 Project Management Plan | bar: Y1 M3 to Y1 M5; Y1 M10; Y2 M11
WP 8.3 Day-to-day coordination activities
Note on I40: Project institutional presentation at P1 16/01/19
Note on I46: CBHE project coordinators meeting in Brussels 27-31/01/19
Note on J32: Quality Assurance Group established 22/02/19
Note on J37: Project website demo version. FB and Twitter pages created
Note on J43: Kick-off meeting held P1, 21-22/02/19
Note on J44: PMB established 22/02/19
Note on K10: Study visit P1-P3 to P5 20-23/03/19
Note on K19: P3 Moodle Platform installed 10/03/19 http://www.filum.kg.ac.rs/moodle/.
Note on K37: Project website developed and launched -Dušanka Jelenković Vidović
Note on K40: Project Info Day at P2 14/03/19
Note on K46: Associated Partnership Agreed with Ministry of Culture and Information of Serbia and Ministry of Education, Science and Technological Development agreed
Note on L9: P3 Internal Assessment of Study Programmes completed 30/05/19
Note on L10: P1-P3 study visit to P6 02-06/04/19; P1-P3 study visit to P4 18-20/04/19
Note on L33: PQAP first draft 14/04/19
Note on L45: Project Management Plan 1st draft 24/04/19
Note on M10: P1-P3 Meeting in Belgrade, 14/05/19 to summarize and exchange experiences and ideas on study visits to P4-P6
Note on M45: PMP adopted 27/05/19
Note on N9: P2 Internal Assessment of Study Programmes completed 12/07/19
Note on N11: Meeting on defining learning outcomes and competencies “Dialogue with the stakeholders”, Novi Sad, 26/06/19, participation of P1-P3, P7-P9
Note on N14: Equipment purchase plan approved by EACEA project officer 20/05/19
Note on N15: Public procurement and tendering procedure launched at P1 28/06/19
Note on N16: Public procurement and tendering procedure launched at P1 28/06/19
Note on N40: DEMUSIS project on Radio Belgrade 1 (P7) Morning show 27/06/2019
Note on N46: 1st Partnership reports submitted to PC
Note on O36: DEP Draft
Note on O40: Project presented at Digital Humanities Oxford Summer School in Oxford (UK) 22-26/07/19
Note on O46: Survey on Implementation Status of the Project completed and submitted 16/07/19
Note on P10: P1-P2 study visit to P4 to plan music entrepreneurship bootcamp 02-06/09/19
Note on Q40: Project presented at AEC IRC Event in Prague, 19-22/09/19
Note on R33: PQAP adopted by PMB 12/11/19
Note on R40: Project presented at the Regional Cluster Meeting CBHE projects’ impact in the Western Balkans in Durres, 22-23/10/19. Project presented 46th AEC Annual Congress and General Assembly, 7-9/11/19
Note on R45: PMP updated on changes in QAG 13/11/19
Note on R46: WB CBHE Regional Cluster Meeting in Durres 22-23/10/19
Note on S15: Repeated Public procurement and tendering procedure for remaining lots launched at P1 25/11/19
Note on S16: Repeated Public procurement and tendering procedure for remaining lots launched at P1 25/11/19
Note on S35: External evaluator’s meeting with QAG 02/12/19
Note on S36: DEP 2nd version
Note on S40: DEMUSIS Team awarded Acknowledgment for exceptional merits and contribution to the work of the Faculty of Music (P1) on 21/11/19. Project and its activities presented in RTS1 Morning Show 21/11/19.
Note on S46: Annual PMB meeting, Novi Sad, 2-3/12/19
Note on T36: DEP 3rd version
Note on T46: 2nd Partnership reports submitted to PC
Note on V19: P2 Moodle platform launched in February 2020. Available at: http://ellab.ftn.uns.ac.rs/
Note on V21: P2 training for distance learning platform eLab/Sova
Note on V33: PQAP update adopted 13/03/20
Note on W18: Purchased hardware, software, digital and other equipment installed and set-up at P1-P3.
Note on W19: Moodle platform adopted for use at P1 in spring 2020. Avaiable at: https://elearning.rcub.bg.ac.rs/moodle
Note on W20: P1-P3 Teacher training study visit to P6 15-21/03 cancelled due to Covid-19
Note on W46: Change in partnership composition P8 Eipix Entertainment to Mad Head Games, submitted for Agency's approval
Note on X40: DEMUSIS project presented at online conference Teaching Music Online in Higher Education 07/05/20
Note on Y9: MusiQuE Institutional Quality Enhancement Review of P1 made public 03/06/20
Note on Y40: Results of project-based research presented at LATIMPE digital platform 13/05/20
Note on Z13: New master program Music Direction at P1 accredited by National Entity for Accreditation 06/07/20
Note on Z46: Online PMB meeting on preparation of TIR and project activities update during covid-19 10/07/20
Note on AA13: New master study program Applied Research in Music at P1 submitted to National Entity for Accreditation 17/07/20
Note on AA46: 3rd Partnership reports submitted to PC
Note on AB35: External evaluator’s interim report 24/08/20
Note on AB36: DEP adopted and published
Note on AB46: Technical Implementation Report submitted to EACEA 31/08/20
Note on AC25: Students enrolled to new two-year master study program Music direction at P1
Note on AC40: Project activities and outcomes in the view of COVID.19 crisis presentated at AEC IRC online event 24-25/09/20 Music Direction study program presented at RTS1 Morning show 15/10/20
Note on AC46: Exceptional online PMB meeting on TIR follow-up, current project activities, issues and plans 17/09/20
Note on AD13: New master program Applied Research in Music at P1 accredited by National Entity for Accreditation 28/10/20
Note on AD25: Students enrolled to new two-semester master study program Applied Research in Music at P1
Note on AD40: Project presented at AEC Annual Congress 6-7/11/20
Note on AE18: Procurement and installation of the remaining hardware and software at P1 and P3.
Note on AE20: Online teacher training P1-P3, P6 02-21/12/20
Note on AE26: Teaching visit Renee Jonker (P4) to P1 new BA course Basics of project planning and music entrepreneurship, and new MA study program Applied Research in Music - 3/12/20 and 17/12/20
Note on AE44: Changes in the PMB composition December 2020
Note on AE45: PMP updated Update of changes in the partnership composition, PMB members, WP chairs, partner contact-persons and administrative staff
Note on AE46: Annual PMB meeting, online, 10-11/12/20
Note on AF20: Online teacher training P1-P3, P5 21-22/12/20
Note on AF21: P1 training for distance learning platform eLearning, 14-18/12/20
Note on AG19: Internal evaluation of the use and needs for further adjustments of the plaftorms
Note on AG38: Academic and financial sustainability plan 1st draft
Note on AH20: P1–P4 meeting regarding organization of teacher training
Note on AH22: P1–P3 meeting for preparation of teaching materials for new and modernized studies and publishing plan - February 2021
Note on AI20: Online teacher training in entrepreneurship P1-P3, P4 19-23 April 2021
Note on AI26: P1–P6 online meeting on P4–P6 online teaching visits to P1–P3 new and modernized courses and P1 new study programs in spring semester 2021 – February 2021
Note on AI28: P1–P3+P7, P1–P3+P10 meeting regarding realization of online and live student practice in 2021 – February 2021
Note on AJ29: P1–P3 meeting on LLL courses preparation - Spring 2021
Note on AK20: Online meetings P1 and P4-P6 (4-8 June 2021) to set live follow-up in 2021/22 to online teacher training realized in 2020/21
Note on AK26: Online teaching visit of P4 teachers to P1-P3 within the entrepreneurial bootcamp "Music - Here and Now" for P1-P3 students of modernized and new study programs 10-24 May 2021
Note on AK40: 1st entrepreneurial bootcamp for music students in Serbia "Music - Here and Now" presented at National Radio 27 May 2021 and TV Morning Show of National Broadcasting Service RTS 11 June 2021
Note on AL30: Preparation of LLL learning materials as planned by project proposal May-June 2021
Note on AL38: Final AFSP developed and published
Note on AL41: 8 student project publicly presented at P1-P3 within entreprenerial bootcamp for music students in Serbia "Music - Here and Now" 10-24 May 2021
Note on AL46: Bilateral partner meetings on project eligibility period extension P1-P10
Note on AO15: Direct purchase of additional video and studio equipment for P3 to ensure better implementation of new and modernized courses
Note on AO25: Second generation of students enrolled to new master study programs Applied Research in Music and Music Direction at P1
Note on AO28: Online student placements at P10 (6 students P1, P3) 6-17.9.2021
Note on AO29: Online meeting P1-P3 working group for WP5: Preparation for the design and accreditation of LLL courses 29.9.2021
Note on AO40: Learning outcomes of the entrepreneurial bootcamp "Music - Here and Now" as an example of cross-curricular learning at HMEI presented at the 24th International Pedagogical Forum for Performing Arts, 2.10.2021
Note on AP29: Call for LLL courses accreditation by National Institute for Promotion of Education (ZUOV)
Note on AQ20: Live follow-up by P5-P6 at P1-P3 to teacher training realized online in 2020/21
Note on AQ28: Live student placements at P7 (5 students P1-P3) end of November 2021; Online student placements (5-10 students P1-P2) at P10 15-26.11
Note on AQ31: Implementation of LLL courses as planned by project proposal October 2021-January 2022
Note on AQ38: Final AFSP developed and published
Note on AQ46: Annual PMB meeting at P3 (hybrid)
Note on AR20: Live follow-up at P1-P3 to teacher training realized online in 2020/21 by P4-P6
Note on AS13: Accreditation of new master study program Music Production at P2
Note on AU20: Live follow-up by P5-Live teacher training follow-up P5-P6 at P1-P3 to teacher training realized online in 2020/21
Note on AV20: Live teacher training follow-up P5-P6 at P1-P3 to teacher training realized online in 2020/21
Note on AW28: Live student placements at P7 (5 students P1-P3)
Note on BA20: Live follow-up to teacher training for entrepreneurial bootcamp P1-P4
Note on BA25: Third generation of students enrolled to new master study programs Applied Research in Music and Music Direction at P1
Note on BA26: Live teaching visit of P4 teachers to P1-P3 within the entrepreneurial bootcamp for P1-P3 students of modernized and new study programs, to be realized within WP 7.7 at P2
Note on BA29: LLL courses accredited by National Institute for promotion of Education
Note on BB28: Follow-up to student placements at P7 and P10 (in the framework of the Public debate in Novi Sad)
Note on BB41: Public presentation of P1-P3 student projects within Novi Sad EU Capital of Culture
Note on BC46: Annual PMB meeting at P1 (live)